## Sheet1
Sprint 3: DLSP - Team 3
| Item | Team Member | Due Date | Status | Comment
Functionality/Validation For Admins |  |  | 2013-11-13
| Deleting courses that have inquiries | Kris |  | Complete
| Editing courses | Kris |  | Complete
| Create reports based on admin's school | Kris |  | Complete
| detect and enforce HTTPS on all pages | Fatema |  | Complete
| Give admins the ability to add Schools to the dropdown list | Kris |  | Complete
| Numeric validations for adding Admin fields | Fatema |  | Complete
| Indication that course was added to the system for uploading excel files | Fatema |  | Complete
| Add course validation for manually inserting courses | Kris |  | Complete
| Sortable gridview for delet courses section | Kris |  | Complete
| Assign multiple schools to admin. | Kris |  | Complete
Prospect Page |  |  | 2013-11-13 | Complete
| Prospects required to choose either YES/NO for Temple Student field | Kris |  | Complete
| Change colors | Fatema |  | Complete
| Text Changes | Fatema |  | Complete
| Search Results: include Online and Campus | Kris |  | Complete
| Sort search by department |  |  | Complete
Prelim User Documentation Assembly |  | Joshua Jodesty | 11/13/2013 @ 5pm | Complete
| The Book | Gordon Li, Joshua Jodesty |  | Complete
| User Manual |  |  | Complete
| Title Page | Fatema |  | Complete
| Table of Contents | Joshua Jodesty, Gordon Li |  | Complete
| System Overview | Joshua Jodesty |  | Complete
| Functions | Gordon Li |  | Complete
| System Requirement | Joshua Jodesty |  | Complete
| Troubleshooting | Joshua Jodesty |  | Complete
| Help Documents | TBD |  | Excluded
| Support/Administrator’s Guide |  |  | Complete
| Network Installation | Gordon Li |  | Complete
| Security | Joshua Jodesty |  | Complete
| Database Management | Joshua Jodesty |  | Complete
| Configuration | Gordon Li |  | Complete
| Backup/Recovery Procedures | Gordon Li |  | Complete
| Support | Gordon Li |  | Complete
| Hosting providers, payment terms | Gordon Li |  | Complete
| Domain name registry and payment terms | Gordon Li |  | Complete
| Purchased software and payment terms | Gordon Li |  | Complete
| Ongoing maintenance and timeframes for it | Gordon Li |  | Complete
| FAQ | Joshua Jodesty |  | Complete
| Quick Refference Guide | TBD
Final User Documantation Assembly | (Above) | Joshua Jodesy | 11/21/2013 @ 5pm | Complete
Testing
| Preliminary Test Plans*********** | Joshua Jodesty | 11/11/2013 @ 5pm | Complete
| Executed Test Plans | Joshua Jodesty | 11/18/2013 @ 5pm | Complete
| Client Testing********* | Dominique | 2013-11-10 | Complete
Misc.
| Security Review | Joshua Jodesy | 2013-11-08 | Complete
| 2 Copys of Documentation for Wendy and Dominique | Joshua Jodesty | 2013-11-25 | Complete
| PowerPoint for Dominique's demo on Nov. 8 | Fatema/Gordon/Joshua | 2013-11-08 | Complete
| Sprint 3 Plan | Joshua Jodesty | 2013-11-30 | Complete
| API | Joshua Jodesty, Gordon Li
Optional | Reports: add reply to the prospect (New), Online, Campus Subcribed * | TBD | 2013-11-13 |  | *This is an added functionality we will only do IF everything else gets Complete
Presentations
| Presentation Draft********* | All | 2013-11-13 | Complete
| Dry Run 1 | All | 2013-11-18 | Complete
| Dry Run 2 | All | 2013-11-20 | Complete
| DLSP Presentation | All | 2013-11-07 | Complete
| Client Presentation | All | 11/25/2013 - (12/2) | Complete